## Q4
Q4
Month | Week | Backend | Difficulty | Frontend | Difficulty
October | 2020-10-23 | learn Python | moderate | learn React | moderate
| 2020-10-30 | learn how Flask works | moderate | learn Redux | moderate
November | 2020-11-06 | create my GitHub repo | easy | create a single page | moderate
| 2020-11-13 | create an Azure account | easy | create a form to submit input | moderate
| 2020-11-20 | create the scaffolding | moderate | define the API calls | moderate
| 2020-11-27 | test the code locally | easy | test locally | moderate
Desember | 2020-12-04 | configure GitHub Actions | moderate | connects to an API | moderate
| 2020-12-11 | setting up Azure Ppelines | some what hard | update the UI | moderate
| 2020-12-18 | test continuous delivery | some what hard | test continuous delivery | moderate
| 2020-12-23 | Backend ready for quality assurance | some what hard | Frontend ready for quality assurance | some what hard
| 2020-12-31 | Backend ready for quality control | hard | Frontend ready for quality control | hard
| 2021-01-08 | Backend ready | - | Frontend ready | -
|  | Goals |  | Goals
|  | Build a ML API with Python and Flask | some what hard | Deployed on Azure | moderate
|  | with a Logging set up | some what hard | using React and Redux | moderate