## 20_21
2020 -2021
[6 empty] | Q4 | [21 empty] | Q1 | [12 empty] | Q2 | [12 empty] | Q3
[6 empty] | October |  |  |  | November | [7 empty] | Desember | [9 empty] | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September
[6 empty] | 23 |  | 30 |  | 6 |  | 13 |  | 20 |  | 27 |  | 4 |  | 11 |  | 18 |  | 23 |  | 31 |  | 8 |  | 15 | 22 | 29 | 5 | 12 | 19 | 27 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 8 | 15 | 22 | 29 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24
Project | [5 empty] | Task ¦ Difficulty | [21 empty] | Task ¦ Difficulty | [12 empty] | Task ¦ Difficulty | [12 empty] | Task ¦ Difficulty
Build a ML API with Python and Flask using React |  |  |  | Path | Frontend | learn React | moderate | learn Redux | moderate | create a single page | moderate | create a form to submit input | moderate | define the API calls | moderate | test locally | moderate | connects to an API | moderate | update the UI | moderate | test continuous delivery | moderate | Frontend ready for quality assurance | some what hard | Frontend ready for quality control | hard | Frontend ready | -
[5 empty] | Backend | learn Python | moderate | learn how Flask works | moderate | create my GitHub repo | easy | create an Azure account | moderate | create the scaffolding | moderate | test the code locally | easy | configure GitHub Actions | moderate | setting up Azure Ppelines | some what hard | test continuous delivery | some what hard | Backend ready for quality assurance | some what hard | Backend ready for quality control | hard | Backend ready | -
Goals | Difficulty | Goals | Difficulty
Build a ML API with Python and Flask | some what hard | Deployed on Azure | moderate
with a Logging set up | some what hard | using React and Redux | moderate